## Maps & Traversal
Subcomponent | Work item | Dependency phase | Depends on | Unlocks / completion impact | Notes on completion
World map | Define campaign geography and region unlocks | 1 - Foundation | Narrative act structure | Provides macro route context for all grand exploration areas | Complete - campaign geography fixed into 3 major areas and 13 numbered locations, with world map placement and stable area/location IDs established.
Map standards | Lock art dimensions, scale rules, route readability, and accepted map types | 1 - Foundation | Current visual spike standards | Prevents every map type from inventing its own contract
Map data contract | Define shared fields for map id, kind, background, nodes, exits, entry points, discovery, and save position | 1 - Foundation | Map standards | Unlocks runtime loading, authoring, validation, and save/load
Grand exploration | Promote node/edge traversal into a player-facing runtime | 2 - Core loop | Map data contract; visual spike traversal prototype | Unlocks vast authored maps with agency
Grand exploration authoring | Keep/refine node placement, edge curves, triggers, labels, discovery state, and save-to-disk workflow | 2 - Core loop | Map data contract | Unlocks efficient content creation for large maps
Map transitions | Define movement between world, grand, local, combat, and scene maps | 2 - Core loop | Map data contract; scene routing | Unlocks stable returns from combat, dialogue, camps, and cutscenes
Discovery model | Implement hidden/revealed nodes, labels, journal/map updates, and persistent memory | 2 - Core loop | Grand exploration runtime; game state flags | Unlocks exploration payoff and quest/map integration
Local exploration | Define tighter scene-scale movement and hotspot interaction for interiors and close spaces | 3 - Expansion | Map transitions; narrative interaction | Unlocks inspectable locations and local NPC/service placement
Combat map handoff | Bind traversal/local nodes to tactical arenas, spawns, return locations, and aftermath state | 2 - Core loop | Combat maps; encounter setup | Unlocks encounter entry and clean post-combat routing
Map UI polish | Add visual states, labels, hover/select feedback, route affordances, and accessibility/readability pass | 4 - Polish | Runtime loops working | Makes the map layer production-facing

## Characters & Party
Subcomponent | Work item | Dependency phase | Depends on | Unlocks / completion impact
Actor contract | Define shared actor identity, stats, resources, conditions, actions, and visual references | 1 - Foundation | Existing character/combat data | Unlocks combat, character sheets, enemy data, saves, and UI
Player character | Stabilize persistent player sheet: ancestry, class, level, abilities, HP, resources, spells, proficiencies | 1 - Foundation | Actor contract | Unlocks combat readiness, checks, inventory, and save continuity
Character creation | Finalize creation steps, validation, derived stats, starting choices, portrait/mini selection, and final handoff | 2 - Core loop | Player character contract | Unlocks new-game flow and representative build testing
Character sheet UI | Make the player sheet readable and editable where appropriate | 2 - Core loop | Player character contract; core UI | Unlocks progression, inventory review, and debug confidence
Progression | Complete level-up choices, class/subclass features, feats, spell learning/preparation, and resource growth | 2 - Core loop | Player character; validation tools | Unlocks longer-form play and build variety
Companions | Define companion recruitment state, sheets, banter hooks, party resources, and combat participation rules | 3 - Expansion | Actor contract; narrative interaction | Unlocks party composition and companion-driven story
NPCs | Define named NPC identity, faction, portrait/marker, dialogue entry, merchant/service role, and map placement | 2 - Core loop | Narrative interaction; map placement | Unlocks populated maps, quests, shops, and services
Enemies | Complete enemy stat blocks, tactical roles, AI behavior hooks, awareness, spawn groups, and reward metadata | 1 - Foundation | Actor contract; encounter rules | Unlocks encounter authoring and combat coverage
Miniatures/tokens | Connect actor records to reliable visual tokens or miniatures | 3 - Expansion | Actor contract; visual direction | Unlocks readable combat and character presentation
Save compatibility | Persist character/party state without breaking older save assumptions | 3 - Expansion | Player character; progression; inventory | Protects long-running playthroughs

## Encounters
Subcomponent | Work item | Dependency phase | Depends on | Unlocks / completion impact
Encounter contract | Define encounter id, map id, enemy groups, spawn rules, trigger source, reward set, and return route | 1 - Foundation | Actor contract; map data contract | Unlocks consistent combat and non-combat encounter authoring
Combat loop | Stabilize start, initiative, turns, action economy, movement, targeting, reactions, conditions, and outcomes | 1 - Foundation | Actor contract; combat maps | Unlocks the main repeatable gameplay loop
Tactical map rules | Finalize movement, cover, elevation, difficult terrain, line of sight, hazards, and area targeting | 1 - Foundation | Combat grid as authority | Unlocks reliable map design and combat balance
Encounter setup | Author enemy groups, actor placement, difficulty intent, narrative trigger, and pre-combat state | 2 - Core loop | Encounter contract; enemy data | Unlocks repeatable scenario creation
Enemy behavior | Implement target selection, movement choice, action/spell choice, group tactics, morale/retreat, and boss scripts | 2 - Core loop | Combat loop; enemy roles | Unlocks tactically credible fights
Traversal encounters | Connect grand/local map nodes to ambushes, warnings, traps, negotiations, and discoveries | 2 - Core loop | Map transitions; encounter contract | Makes traversal consequential
Rewards and aftermath | Apply loot, quest updates, area state changes, post-combat dialogue, and return routing | 2 - Core loop | Inventory; narrative interaction; map transitions | Closes the combat loop cleanly
Non-combat encounters | Support skill checks, traps, social resolution, camp interruptions, and exploration events | 3 - Expansion | Narrative interaction; character checks | Adds variety outside tactical fights
Encounter validation | Check actors, spawns, maps, rewards, and return routes for broken contracts | 2 - Core loop | Encounter contract | Prevents content from silently breaking runtime loops
Balance and polish | Tune difficulty, pacing, enemy mix, rewards, visual feedback, and combat readability | 4 - Polish | Working combat and encounter content | Makes encounters feel finished

## Narrative
Subcomponent | Work item | Dependency phase | Depends on | Unlocks / completion impact
Story spine | Clarify acts, major locations, core conflicts, faction pressure, and required playable beats | 1 - Foundation | Design/lore docs | Guides maps, quests, NPCs, and progression pacing
Dialogue contract | Define dialogue id, speaker, choices, gates, effects, route exits, and state writes | 1 - Foundation | Scene routing; game state | Unlocks dialogue authoring and validation
Dialogue UI | Make speaker identity, text, choices, disabled gates, and consequence hints readable | 2 - Core loop | Dialogue contract; core UI | Unlocks playable conversations
Quest structure | Define objectives, states, completion/failure rules, branch outcomes, and journal updates | 1 - Foundation | Story spine; game state | Unlocks purposeful traversal and rewards
Inspection | Author hotspot text, clues, environmental storytelling, lore reveals, and state-gated descriptions | 2 - Core loop | Map hotspots; quest structure | Gives maps meaning beyond movement
Factions/reputation | Define faction identities, relationship flags, visible consequences, access changes, and quest branch effects | 3 - Expansion | Story spine; quest structure | Unlocks systemic narrative consequences
Cutscenes | Support system cutscene beats, transitions, text/camera staging, and handoff to dialogue/combat/maps | 3 - Expansion | Scene routing; story spine | Unlocks major authored story moments
Services/social actions | Integrate merchants, rest keepers, trainers if used, and service availability through dialogue/state | 2 - Core loop | NPCs; inventory/economy | Connects narrative characters to game functions
Journal | Show active/completed quests, discoveries, clues, lore, and map-linked objectives | 2 - Core loop | Quest structure; discovery model | Lets players understand goals and consequences
Content pass | Write and review the actual conversations, quest beats, inspection text, and consequences | 4 - Polish | All narrative contracts working | Turns systems into authored game experience

## Inventory Economy
Subcomponent | Work item | Dependency phase | Depends on | Unlocks / completion impact
Item contract | Define item id, type, rarity, stackability, equip/use rules, inspect text, and state effects | 1 - Foundation | Character and combat contracts | Unlocks equipment, loot, shops, and quest items
Equipment | Implement weapons, armor, accessories if used, equip rules, proficiencies, derived stats, and combat actions | 1 - Foundation | Item contract; actor contract | Unlocks build expression and combat loadouts
Consumables | Support potions, scrolls, tools, food/travel supplies, combat/non-combat use, stack counts, and restrictions | 2 - Core loop | Item contract; combat/narrative use hooks | Adds tactical and exploration resource decisions
Unique/quest items | Support named artifacts, clues, locks, one-off effects, visibility rules, and persistence | 2 - Core loop | Item contract; quest structure | Unlocks narrative gating and authored rewards
Inventory UI | Display carried items, filters, equipment slots, item details, use/equip/drop actions, and error states | 2 - Core loop | Item contract; core UI | Makes items usable by players
Loot | Define containers, post-combat rewards, placed pickups, loot tables, rarity, and inventory handoff | 2 - Core loop | Item contract; encounters | Closes reward loop for exploration and combat
Merchants | Define shop inventory, prices, buy/sell rules, stock state, service gating, and dialogue integration | 3 - Expansion | Inventory UI; NPC services | Unlocks economy and service NPCs
Currency | Define sources, sinks, pricing bands, reward pacing, scarcity, and balance pressures | 3 - Expansion | Loot; merchants; progression pacing | Makes rewards and shops coherent
Economy validation | Check missing item refs, invalid equip rules, broken shop entries, and impossible rewards | 2 - Core loop | Item contract | Prevents content drift
Balance and polish | Tune item availability, consumable value, unique rewards, prices, and progression pressure | 4 - Polish | Working inventory/economy loop | Makes the economy feel intentional

## Presentation Shell
Subcomponent | Work item | Dependency phase | Depends on | Unlocks / completion impact
Core UI framework | Establish shared layout, typography, controls, overlays, focus states, and input affordances | 1 - Foundation | Current app shell | Unlocks consistent screens across the game
Game screens | Main menu, settings, save/load, character creator, character sheet, inventory, journal, map views, dialogue UI, combat HUD, rest/camp UI | 2 - Core loop | Core UI framework; relevant contracts | Turns systems into accessible player surfaces
Feedback language | Define toasts, combat log, damage/healing text, selection highlights, invalid action messages, and confirmations | 2 - Core loop | Core UI; combat/narrative events | Makes state changes legible
Save/load shell | Provide save slots, load validation, error handling, continuity messaging, and recovery paths | 2 - Core loop | Game state contracts | Protects play sessions and testing
Visual direction | Set map art style, character art direction, tokens/miniatures, lighting/fog, VFX, transitions, and palette discipline | 1 - Foundation | Current visual assets and target tone | Guides all production assets
Audio direction | Define music states, ambient loops, UI sounds, combat cues, discovery stingers, and volume settings | 3 - Expansion | Map/encounter/narrative state events | Adds mood and feedback
Production asset checks | Track placeholders, missing images/audio, inconsistent dimensions, and invalid asset refs | 2 - Core loop | Validation tools; asset manifests | Prevents prototype assets from shipping
Performance | Check load time, image sizes, render cost, memory pressure, and combat/map responsiveness | 3 - Expansion | Representative content loaded | Keeps the playable build viable
Packaging | Electron packaging, app metadata, file paths, production build assumptions, and platform checks | 4 - Polish | Working game loop; validation passing | Makes the game distributable
Regression readiness | Validation, smoke tests, representative saves, content checks, and release checklist | 3 - Expansion | Major contracts established | Lets us make changes without breaking the build